## 5A. Content Schedule Format
No. | Item | Description | Responsibility | Recommendation | Due Date | Formula | Assigned To | Status | Notes
5.01.00 | Scope, context, and organizational readiness established | Review items from Part 1 | All | ASAP / Ongoing
5.01.01 | Agile Teams Defined | All Team members are assigned to an agile team which is appropriately sized and Product Owners and Scrum Masters/Team Coaches are identified | Organization Leadership | Reviewed Each PI | 2023-04-04 | ParmPIStart-63
5.01.02 | Key Agile Roles Identified | The following roles have been assigned: Release Train Engineer, Product Management, System Architect and appropriate time is allocated to responsibilities (preferably 100% dedicated) | Organization leadership | Reviewed Each PI | 2023-04-04 | ParmPIStart-63
5.01.03 | Product Vision | Product Vision is created, reviewed, updated as appropriate | Product Management | Reviewed Each PI | 2023-04-11 | ParmPIStart-56
5.01.04 | System Team and UX | System Team and UX members are identified and availability and needs have been clarified | Organization Leadership | Reviewed Each PI | 2023-04-04 | ParmPIStart-63
5.01.05 | Product Backlog Created | Product Backlog Workshop is held with Product Management, Product Owner, Customers, Management and Scrum Masters/Team Coaches | Product Management Facilitated by RTE | Hold workshop as needed. Particularly if ART Backlog is insufficient or unrefined | Ongoing | Ongoing
5.01.06 | Value Stream Mapping | Activity engaging Product Management, Organization Leadership, System Architect to create a long-lived series of steps that deliver value from concept to delivery. | Facilitated by RTE | Workshop as needed, review for each PI | 2023-04-11 | ParmPIStart-56
5.01.07 | ART Working Agreement | Agreement activities AND guidelines that will be abided by. High level and adoptable by all ART members | Facilitated by RTE | Reviewed Each PI | 2023-04-11 | ParmPIStart-56
5.01.08 | ART Definition of Done | Agreed upon list of activities that are necessary to complete the PI. High Level DOD that all teams are expected to meet. | Facilitated by RTE | Reviewed Each PI | 2023-04-11 | ParmPIStart-56
5.02.00 | Final agenda | Final agenda with start and stop times, timeboxes, speaker callouts, etc. Take into account time zone differences if the planning meeting is spread across multiple locations. | Release Train Engineer | 3 Weeks Before PI
5.02.01 | Schedule | Finalize PI Event Schedule including start / stop times accounting for multiple time zones if necessary | Release Train Engineer | 3 weeks prior to PI | 2023-05-16 | ParmPIStart-21
5.02.02 | Identify Presenters | Identify presenters and notify them of their responsibilities and due dates | Release Train Engineer | 6 weeks prior to PI | 2023-04-25 | ParmPIStart-42
5.03.00 | Facilitator preparation | Facilitators understand context and mechanics of event, and facilitator guidelines. For the first PI Planning meeting, if the Release Train Engineer is not an SPC, he or she will need to be paired with an SPC in order to use the PI Planning Toolkit. | Facilitator/ Release Train Engineer | 1 Week Before PI
5.03.01 | Complete Readiness Workbook | Review and work through Readiness workbook. Continuously improving it by adding, updating and removing items as necessary. | Release Train Engineer | Ongoing | Ongoing | Ongoing
5.03.02 | Facility Reservations | Ensure that facilities have been reserved and that there is enough space to accommodate the teams. See 6. Facilities tab in ART Readiness Workbook | Release Train Engineer | As soon As Possible | 2023-03-28 | ParmPIStart-70
5.03.03 | Supplies | Ensure that Supplies are on hand at the PI event for each team. Order if necessary. See 7. Supplies tab in ART Readiness Workbook | Release Train Engineer | 6 weeks before to PI | 2023-04-25 | ParmPIStart-42
5.03.04 | Create PI Slide Deck | Ensure that the PI Slide deck is created and in a location where presenters can update it. If reusing, delete any information for current PI to give presenters a blank slate to add content | Release Train Engineer | 2 Weeks after PI event | 2023-04-11 | ParmPIStart-56
5.03.05 | PI Slide Deck Finalized | Ensure that slide deck materials are complete and accurate. Copy to local device to prevent network access issues | Release Train Engineer | Day before PI event | 2023-06-04 | ParmPIStart-2
5.03.06R | Remote Technology Identified | Ensure that technology is identified and tested to support remote PI Planning, including breakout rooms, conference lines, ART Boards, Team Boards, etc. | Release Train Engineer | As soon As Possible | 2023-03-28 | ParmPIStart-70
5.03.07R | Remote Technology Training | Ensure that ART team Members are familiar with Technology and are able to navigate and use technology systems for PI Planning | Release Train Engineer | 1 week before PI | 2023-05-30 | ParmPIStart-7
5.04.00 | Introductory briefing | Establishes schedule, objectives, context, and requirements for session. | Facilitator/ Release Train Engineer | 2 Weeks Before PI
5.04.01 | Intro Briefer Identified | Identify who will present the introduction to the PI event | Release Train Engineer | at least 6 weeks before PI | 2023-04-25 | ParmPIStart-42
5.04.02 | Intro Briefer Responsibilities | Establishes schedule, objectives, context, requirements for session | Introduction Briefer | at least 6 weeks before PI | 2023-04-25 | ParmPIStart-42
5.04.03 | PI Slide Deck - Introductory Briefing | Update the PI Slide deck | Briefer | at least 1 week before PI | 2023-05-30 | ParmPIStart-7
5.05.00 | Executive briefing | Defines current business context. | Executive identified | 2 Weeks Before PI
5.05.01 | Executive Briefer Identified | Identify who will present the Executive Briefing to the PI event | Release Train Engineer | at least 8 weeks before PI | 2023-04-11 | ParmPIStart-56
5.05.02 | Executive Briefer Resonsibilities | Defines current business context and investment themes | Executive Briefer | at least 8 weeks before PI | 2023-04-11 | ParmPIStart-56
5.05.03 | PI Slide Deck - Executive Briefing | Update the PI Slide deck | Executive Briefer | at least 1 week before PI | 2023-05-30 | ParmPIStart-7
5.06.00 | Product Vision briefing(s) | Briefings prepared by Product Management. Handouts/backlogs prepared with supporting detail (Features, priorities, market reports, use cases, UX guidelines, etc.). | Product Managers and Business Owners | 2 Weeks Before PI
5.06.01 | PI Vision | Optional - Some ARTS like to have a vision or goal for each PI to help align the ART. Similar to Product Vision, but timeboxed to PI. | Product Management | 3 weeks before PI | 2023-05-16 | ParmPIStart-21
5.06.02 | PI Slide Deck - Product Vision Section | Once Epics and Features for PI are determined. PM can update the PI Presentation slide deck with the ART Epics and any other additional Product Vision Information | Product Management | At least 2 weeks before PI | 2023-05-23 | ParmPIStart-14
5.06.03 | PI Slide Deck - Product Vision Section | Once the Features are identified, update slides reflecting details for the features including business hypothesis. | Product Management Product Owners | At least 2 weeks before PI | 2023-05-23 | ParmPIStart-14
5.07.00 | ART Backlog | Top 10 Features. To prepare, review Vision, understand Strategic Themes, and gain alignment with product strategies. | Product Managers and Product Owners | 6 Weeks Before PI
5.07.01 | PI Features Identified and Prioritized | Features for next PI are identified | Product Management | 6 to 8 weeks before PI event | 2023-04-25 | ParmPIStart-42
5.07.02 | ART Backlog Refinement | ART Backlog is decomposed/refined with Features, Benefit Hypothesis and Acceptance Criteria | Product Management Product Owners | 6-8 weeks prior to PI event (rolling refinement preferred) | 2023-04-11 | ParmPIStart-56
5.07.03 | Feature Decomposition | Work with teams to begin to create stories for each feature. Note: Stories do not have to be "Ready" but should have enough information to allow for rough sizing | Product Owners | At least 4-6 weeks prior to PI Event (rolling refinement preferred) | 2023-05-30 | ParmPIStart-7
5.07.04 | Story Print Outs | Print stories for the features to the PI event. Print on paper or sticky notes that matches the story sticky note color (ex. green) | Scrum Masters/Team Coaches | 1 day before PI | 2023-06-04 | ParmPIStart-2
5.07.05R | Story Exports | Export / Import Stories or ensure linkage to Agile Tool | RTE & Scrum Masters/Team Coaches | 1 Week before PI | 2023-05-30 | ParmPIStart-7 |  |  | Test 1 week prior, export/import 1 day before
5.08.00 | Architectural Vision briefing | Communicate any new architectural Epics and system quality (nonfunctional) requirements. | CTO/Architects, Security Directors, etc. | 2 Weeks Before PI
5.08.01 | PI Slide Deck - Architectual Vision Section | Update the slide deck with information relevant to the PI for the teams. Items to consider are: Architectural Vision Statement, Solution Context, Solution Intent. Non-Functional Requirements, Compliance items, Architectural Roadmap, etc | System Architect | 2 weeks before PI | 2023-05-23 | ParmPIStart-14
5.09.00 | Development practices briefing | Changes to standard practices, new tools (Agile project management tool, test automation, Continuous Integration), expectations for the "definition of done," etc. | Sr. Development Management | 2 Weeks Before PI
5.09.01 | PI Slide Deck - Development Practices Briefing | May be combined with Architectual Briefing. Additional topics to consider, DevOps, CI/CD, coding standards, Automated Testing, System Outages, etc. | System Architect | 2 weeks before PI | 2023-05-23 | ParmPIStart-14
5.10.00 | Meeting notice | Finalize agenda and send meeting notice to attendees with venue, access requirements, etc. | Release Train Engineer | Place Holder Immediately after Previous PI - Final Notice 4 Weeks Before PI
5.10.01 | PI Save The Date | Send a note out to PI Participants to save the date for the PI event | Release Train Engineer | Immediately after PI event | 2023-03-28 | ParmPIStart-70
5.10.02 | PI Meeting Invite | Send the calendar invite to all attendees. Include Travel information if needed. Advise attendees of start and end times, dress code, access requriements, etc. | Release Train Engineer | At least 4 weeks prior to Event | 2023-05-09 | ParmPIStart-28
5.10.03 | PI Custom Meeting Invites | Send invites to Executives for specific sessions they should attend (ex. Briefings, Plan Readouts, etc) | Release Train Engineer | At least 4 weeks prior to Event | 2023-05-09 | ParmPIStart-28
5.11.00 | Iterations and PI events schedule | Based on Iterations and PI cadence, finalize calendar. Teams events include: Iteration Planning, Iteration Review, Iteration Retrospective. ART events include: PI Planning, System Demo, Inspect & Adapt, Coach Sync, and PO Sync. | Release Train Engineer | 4 Weeks Before PI - should be set a year in advance
5.11.01 | ART and Team Events Calendar Workbook | Complete / Update ART calendar spreadsheet. Resolve any holiday conflicts. Recommend to create and update for a year in advance | Release Train Engineer | Update/Extend after each PI | 2023-03-28 | ParmPIStart-70
5.11.02 | Team Events | Send Invites for Team ceremonies (Daily Standup, Iteration Planning, Iteration Review, Retrospective, Backlog Refinement) | Scrum Masters/Team Coaches | 3 Weeks before PI Event for Next PI | 2023-05-16 | ParmPIStart-21
5.11.03 | ART Events | Send Invites for ART ceremonies (System Demos, PI Pre-Planning, etc) | Release Train Engineer | 3 Weeks before PI Event for Next PI | 2023-05-16 | ParmPIStart-21
5.11.04 | PO Events | Send Invites for PO Sync | Product Manager | 3 Weeks before PI Event for Next PI | 2023-05-16 | ParmPIStart-21
5.11.05 | Architecture Events | Send Invites for Architecture Sync | System Architect | 3 Weeks before PI Event for Next PI | 2023-05-16 | ParmPIStart-21
5.11.06 | Scrum Master/Team Coach Events | Send Invites for Coach Sync | Release Train Engineer | 3 Weeks before PI Event for Next PI | 2023-05-16 | ParmPIStart-21
5.12.00 | PI Event Activities | Verify, Validate and Prepare for Event | Release Train Engineer | Before PI Event
5.12.01 | Verify Facilities | Visit Facility and ensure proper setup for tables, etc as well as technology, mics, network connectivity, etc. | Release Train Engineer | Day Before PI | 2023-06-04 | ParmPIStart-2
5.12.02 | Verify Technology | Ensure that the proper technology is available and participants have access. | Release Train Engineer | 2 Weeks Before PI | 2023-05-23 | ParmPIStart-14
5.12.03 | Print out PI Signs & Handouts | Print out any signs that will be needed for the event. See list on Tab 7 | RTE & Scrum Masters/Team Coaches | Day Before PI | 2023-06-04 | ParmPIStart-2
5.12.04 | Set Up Team Space | Set up each of the Team Board Areas following legend | Scrum Masters | Day Before PI | 2023-06-05 | ParmPIStart-1
5.12.05R | Set up Team Space - Remote | Ensure each of the team boards are configured in the tooling | Scrum Masters | 2 Weeks Before PI | 2023-05-23 | ParmPIStart-14
5.12.06 | Set up ART Board | Create the ART Board following legend | Release Train Engineer | Day Before PI | 2023-06-05 | ParmPIStart-1
5.12.07R | Set up ART Board - Remote | Ensure the ART board is set up and configured in tooling | Release Train Engineer | 2 Weeks Before PI | 2023-05-23 | ParmPIStart-14
5.12.08 | Arrive Early | Arrive early to the PI event to ensure boards have not fallen down and to connect/validate technology | RTE & Scrum Masters/Team Coaches | Day of PI event | 2023-06-06 | ParmPIStart
5.12.09R | Populate Agile PI Tool | Populate or Ensure Agile Tool has all stories, features etc available in the tool | RTE & Scrum Masters/Team Coaches | Day Before PI | 2023-06-05 | ParmPIStart-1
5.13.00 | Inspect & Adapt Workshop | Current state of solution is demonstrated and teams reflect and identify improvement backlog items. | Release Train Engineer | Before PI Event
5.13.01 | I&A Save The Date | Send a note out to I&A Participants to save the date for the I&A event | Release Train Engineer | Immediately after PI event | 2023-03-27 | ParmIADate-70
5.13.02 | I&A Meeting Invite | Send the calendar invite to all attendees. Include Travel information if needed. Advise attendees of start and end times, dress code, access requriements, etc. | Release Train Engineer | At least 4 weeks prior to Event | 2023-05-08 | ParmIADate-28
5.13.03 | I&A Custom Meeting Invites | Send invites to Executives for specific sessions they should attend (ex. System Demo) | Release Train Engineer | At least 4 weeks prior to Event | 2023-05-08 | ParmIADate-28
5.13.04 | Create Slide Deck | Create Slide Deck Template with place holders | Release Train Engineer | 6-8 Weeks before I&A | 2023-04-24 | ParmIADate-42
5.13.05 | Prepare teams for System Demo | Meet with PO/PM to identify features to demo | RTE, PM, PO, others | 2 weeks before | 2023-05-22 | ParmIADate-14
5.13.06 | Dry run the System Demo | Complete a Dry run of the demo to ensure it fits in the timebox (1 hour) and to work out any kinks | RTE, PM, PO, others | 1 week before | 2023-05-29 | ParmIADate-7
5.13.07 | Complete ART Predictability Measure | Complete the ART Predictability Measure workbook. | Release Train Engineer | Begininng of IP Iteration | 2023-05-31 | ParmIPStart
5.13.08 | Team Self Assessment | Work with Scrum Masters/Team Coaches to condut Team Self Assessments - Recommend during last Iteration retros | RTE & Scrum Masters/Team Coaches | End of Last Iteration | 2023-05-30 | ParmIPStart - 1
5.13.09 | Compile Team Metrics into Slide Deck | Ensure the following Metrics are included: ART Predictability Measure, Team Performance Assessments, Team Performance Reports, ART Performance Metrics | Release Train Engineer | During IP Iteration | 2023-05-31 | ParmIPStart
5.13.10 | Finalize Slide Deck | Ensure that all Slide deck is finalized and demo, metric and retro information is included. | Release Train Engineer | At least 1 Day before Event | 2023-06-03 | ParmIADate-2
5.13.11 | I&A Workshop Boards | Print out / Create and Boards, signage, instructions for Problem Solving Workshop | Release Train Engineer | 1 week before | 2023-05-29 | ParmIADate-7
5.13.12 | Set up room | Ensure the room is set up and any handouts / boards are created to facilitate meeting | Release Train Engineer | Day Before Event | 2023-06-04 | ParmIADate-1
5.13.13R | Set up Tools - Remote | Ensure that Tools are setup and configured to support the Problem Solving Workshop | Release Train Engineer | 1 week before | 2023-05-29 | ParmIADate-7
5.14.00 | Training | Ensure that all participants have had training / SAFe Certifications as applicable | Release Train Engineer | As Needed and Planned for
5.14.01 | All ART Participants | Leading SAFe (SA) and/or SAFe for Teams (SP) | Management | As Needed
5.14.02 | Developers | SAFe Agile Software Engineering (ASE) | Management | As Needed
5.14.03 | Scrum Master/Team Coach | SAFe Scrum Master (SSM) and/or SAFe Advanced Scrum Master (SASM) | Management | As Needed
5.14.04 | Release Train Engineer | SAFe Release Train Engineer (RTE) and Implementing SAFe (SPC) | Management | As Needed
5.14.05 | Product Management | SAFe Product Owner/Product Manager (POPM) | Management | As Needed
5.14.06 | Product Owners | SAFe Product Owner/Product Manager (POPM) | Management | As Needed
5.14.07 | Developers, System Team | SAFe DevOps (SDP) | Management | As Needed
5.14.08 | System Architect | SAFe for Architects (ARCH) | Management | As Needed
5.14.09 | Program Management, Organization Leadership | Leading SAFE (SA) and Lean Portfolio Management (LPM) | Management | As Needed

## 8. Parameters
© Scaled Agile, Inc.
Supplies Parameters
Parameters for Calculations | Count | Comments
Number of total team tables | 10
Number of total team members | 100
Number of guests | 40
Remote locations to video in | 2
PI Event Start Date | 2023-06-06
I&A Date | 2023-06-05
Number of Iterations in PI | 5
IP Iteration Start Date | 2023-05-31